Based on your project proposal, the current date (Feb 5th), and the deadline (March 23rd for the report, March 30th for the presentation), I have designed a structured project plan.

This plan integrates the "Champion-Challenger" methodology (XGBoost vs. LSTM) outlined in your proposal and balances the workload to ensure Hosanna and Amy get the technical practice they want while leveraging Mohammad and Suhail's strengths for the complex architecture.

### 1. Team Roles & Responsibilities

- Mohammad & Suhail (Technical Leads): Responsible for the core architecture of the LSTM, the custom WMAE loss function, and the complex preprocessing pipeline (Entity Embeddings).

- Hosanna (Project Manager & Data Analyst): Responsible for the Backlog management, interpreting model results (SHAP values), and writing the Executive Summary. Practice Area: Running the XGBoost baseline and tuning hyperparameters.

- Amy (Narrative Lead & Feature Engineer): Responsible for the Jupyter Notebook narrative, drafting the report, and Presentation design. Practice Area: Feature engineering (creating lags, holiday flags) and data cleaning.

### 2. The Sprint Schedule (Feb 5 – Mar 30)

We will treat the time remaining as 3 Sprints (2 weeks each) plus a final "Delivery Sprint".

| Sprint | Dates | Focus | Key Deliverable |
| --- | --- | --- | --- |
| Sprint 1 | Feb 6 – Feb 19 | Pipeline & Baseline | Cleaned Data & XGBoost Baseline |
| Sprint 2 | Feb 20 – Mar 5 | Deep Learning Implementation | Working LSTM Model |
| Sprint 3 | Mar 6 – Mar 19 | Evaluation & Reporting | Final Results, SHAP Analysis, Draft Report |
| Sprint 4 | Mar 20 – Mar 30 | Final Polish & Presentation | Submitted Report & Slide Deck |

### 3. Detailed Biweekly & Weekly Task Breakdown

#### Sprint 1: The Foundation (Feb 6 – Feb 19)

Goal: Complete the "Data Ingestion" and "Feature Engineering" components and establish the XGBoost baseline.

Sprint To-Do List:

- Build Preprocessing Pipeline (Z-score scaling, Binary Masking).

- Generate Lag Features & Holiday Flags.

- Train baseline XGBoost model.

- PM Task: Update Backlog for Sprint 1.

| Who | Week 1 (Feb 6 - 12): Data Prep | Week 2 (Feb 13 - 19): Baseline Modeling |
| --- | --- | --- |
| Mohammad | Dev: Write the "Binary Masking" function for Markdown 1-5 to handle the missing data gap. | Dev: Implement the custom Holiday-Weighted Loss function (5x penalty for holidays) for XGBoost. |
| Suhail | Dev: Code the Z-score normalization pipeline for continuous inputs (CPI, Fuel, etc.). | Dev: Set up the "Champion-Challenger" validation framework (splitting train/test sets to respect time series). |
| Hosanna | PM: Initialize the Excel Backlog. Practice: Write script to load data and merge the features.csv with sales.csv. | Practice: Train the initial "naive" XGBoost model using the data prepared by Amy/Suhail to see initial error rates. |
| Amy | Practice: Create the "Holiday Proximity" features (days until Christmas/Super Bowl) using Pandas. | Writing: Draft the "Data Acquisition & Description" section for the final notebook, explaining the cleaning steps. |

#### Sprint 2: The Deep Learning Core (Feb 20 – Mar 5)

Goal: Implement the LSTM "Challenger" model and Entity Embeddings.

Sprint To-Do List:

- Build Entity Embedding layers for Store/Dept.

- Train LSTM model.

- Compare WMAE of XGBoost vs. LSTM.

- PM Task: Update Backlog for Sprint 2.

| Who | Week 3 (Feb 20 - 26): Architecture | Week 4 (Feb 27 - Mar 5): Training & Tuning |
| --- | --- | --- |
| Mohammad | Dev: Build the PyTorch/TensorFlow definition for the LSTM network, specifically the sequence input layer. | Dev: Run training loops for LSTM on GPU (Colab/Local) and monitor loss convergence. |
| Suhail | Dev: Implement Entity Embeddings for the 45 Stores and 99 Departments (categorical to dense vector). | Dev: Troubleshoot "Model Divergence" (check if gradients are exploding in Dept 72/Electronics). |
| Hosanna | Practice: Pair with Suhail to inspect the Embedding layers—visualize them to see if similar stores cluster together. | PM: Update backlog with "In Progress" tasks. Practice: Help tune hyperparameters (learning rate, hidden units) for the LSTM. |
| Amy | Writing: Start documenting the "Methodology" section of the report (explaining why you chose LSTM vs XGBoost). | Practice: Run the Prophet baseline model to act as a sanity check against the complex models. |

#### Sprint 3: Evaluation & Interpretation (Mar 6 – Mar 19)

Goal: Interpret results using SHAP, finalize WMAE metrics, and write the bulk of the report.

Sprint To-Do List:

- Generate SHAP plots to explain Markdown effectiveness.

- Finalize the Executive Summary (2 pages).

- Clean up the Jupyter Notebook.

- PM Task: Update Backlog for Sprint 3.

| Who | Week 5 (Mar 6 - 12): Analysis | Week 6 (Mar 13 - 19): Reporting |
| --- | --- | --- |
| Mohammad | Dev: Generate the final WMAE scores for both models, specifically isolating Holiday Weeks vs. Normal Weeks. | Dev: Clean code in the Jupyter Notebook. Add comments so Hosanna/Amy understand every line. |
| Suhail | Dev: Run SHAP analysis on the best model to find which Markdowns drove sales. | Dev: Create high-quality visualizations of the Forecast vs. Actuals for the report. |
| Hosanna | Analysis: Interpret Suhail’s SHAP plots—write the business insights (e.g., "Markdown 3 drives sales, but Markdown 1 does not"). | Writing: Write the Executive Summary(2 pages). This is the most critical part for grading. |
| Amy | Writing: Assemble the "Analysis & Results" section. Combine the text with the graphs Mo/Suhail produced. | Writing: Polish the full PDF Report. Ensure all citations are correct and the tone is professional. |

#### Sprint 4: Final Deliverables (Mar 20 – Mar 30)

Goal: Submit Report (Mar 23) and Ace Presentation (Mar 30).

Sprint To-Do List:

- Submit Final Report & Notebook (Due Mar 23).

- Create Slide Deck.

- Rehearse Q&A.

| Who | Week 7 (Mar 20 - 23): Submission | Week 8 (Mar 24 - 30): Presentation |
| --- | --- | --- |
| Mohammad | Final Check: Verify the Jupyter Notebook runs from top to bottom without errors. | Pres: Prepare to answer technical questions about the LSTM architecture and Loss Function during Q&A. |
| Suhail | Final Check: Ensure the WMAE calculation logic is clearly visible and correct in the notebook. | Pres: Prepare to answer questions about the Data Cleaning/Imputation decisions. |
| Hosanna | PM: Submit the Project Backlog (must be complete) and the Final Report/Notebook files. | Pres: Design the slides for "Business Context" and "Strategic Recommendations." Lead the Q&A strategy. |
| Amy | Writing: Final proofread of the PDF report (grammar, flow, formatting). | Pres: Design the slides for "Methodology" and "Results." Ensure the story flows logically. |

### Critical Success Factors (The "Backlog" Reminder)

You noted a hard requirement for a biweekly backlog.

- Hosanna (PM): Set a recurring calendar reminder for every second Sunday to sit with the team for 15 minutes and update the "Status" column in the Excel sheet.

- Grading Alert: The backlog is worth 10% of your grade. Do not fake this at the end; the professor expects meaningful updates every 2 weeks.